## Slide 1
Patio Expansion 2027
Sidewalk build-out proposal for the spring season
Prepared by Carlton McGee / Eleanor's Tavern, Astoria / October 2026

## Slide 2
CONTEXT
Why now
Eleanor's Tavern | Patio Expansion 2027
Page 1
• The 24 seat sidewalk patio runs April through October and lifts covers on every warm night.
• The current furniture is at the end of its life and the awning no longer covers shoulder season weather.
• A spring 2027 build lands before the next patio opening and uses the 2026 operating surplus.
• Same permitted footprint, no change to the lease, no structural attachment to the building.
24
seats on the public way
$42,000
total project budget

## Slide 3
WHAT GETS BUILT
Scope of work
Eleanor's Tavern | Patio Expansion 2027
Page 2
• New pressure treated decking and railing
• Retractable awning for shoulder season cover
• Weatherproof tables and chairs, 24 seats
• Four propane patio heaters
• Licensed lighting and electrical
• Street side planters and screening

## Slide 4
WHERE THE MONEY GOES
Budget breakdown
Eleanor's Tavern | Patio Expansion 2027
Page 3
Line item | Estimate
Decking and railing | $11,500
Retractable awning | $8,900
Outdoor furniture | $6,400
Site survey and permits | $4,200
Lighting and electrical | $3,600
Contingency | $3,100
Outdoor heaters | $2,800
Planters and screening | $1,500
Chart: 
| Deck | Awning | Furniture | Permits | Lighting | Other
Estimate | 11500 | 8900 | 6400 | 4200 | 3600 | 7400

## Slide 5
FROM PLAN TO OPEN
Timeline
Eleanor's Tavern | Patio Expansion 2027
Page 4
Window | Milestone | Owner
November 2026 | Lock scope and request contractor bids | Carlton
December 2026 | Approve budget at the monthly review | Carlton and Ellen
February 2027 | Permits filed, trades scheduled | Carlton
March 2027 | Decking, railing, and electrical | Licensed trades
Early April 2027 | Furniture, awning, final inspection | Carlton
April 2027 | Patio opens for the season | Front of house

## Slide 6
THE CASE
Funding and return
Eleanor's Tavern | Patio Expansion 2027
Page 5
• Funded in full from the restaurant operating surplus built through 2026, no new debt.
• Patio covers carry a strong margin on warm nights and extend the usable season.
• Refreshed furniture and a working awning reduce weather cancellations in spring and fall.
• Approval needed at the December monthly review before any contractor deposit goes out.