## Refit Tracker
SANCTUARY PLATFORM REFIT — cost tracker (CHG0002101)
kept by J. Harris ¦ last touched 7 Oct 2026
Scope item | Approved | Committed | Status at last walk | Note
(a) choir stand tiers rebuild + refinish | 4200 | 4,200.00 | signed off 02/10/26
(b) pipe facade screens, both walls | 1850 | 1,850.00 | signed off 02/10/26
(c) strip carpet, lay sealed oak | 6400 | 6,400.00 | open | oak was back-ordered once
(d) return grand to platform + re-level | 0 | 0.00 | open | in the package, no separate line
(e) clear plant + barriers, hand back | 0 | 0.00 | open | end date 9 Oct
change order WMA-2214 |  | see vendor ledger | NOT REVIEWED | amount not posted here yet
Approved package total | 12450
Instrument maint. remaining (FY26) |  | 3,200.00
TODO check w/ Michael — anything over the standing limit goes to Amanda before it moves, committee sits the 22nd
change order is NOT in the approved total above. do not fold it in until it's reviewed