## Slide 1
COLLECTION DIGITISATION INITIATIVE
Phase 2 Progress Review
Prepared by Stefan Koenig, Deputy Director
For the executive team, reporting period to February 2026
Funded by the EU cultural heritage programme

## Slide 2
Where we are
11,840
objects digitised
of 18,500 in scope
64%
of phase 2 complete
up 9 points this quarter
2,360
objects per month
average capture rate
97%
first pass QC
approved without rework

## Slide 3
Cumulative capture
Objects digitised since the start of phase 2
1,200
Oct 2025
3,500
Nov 2025
5,900
Dec 2025
8,600
Jan 2026
11,840
Feb 2026

## Slide 4
Progress by collection area
Photography
83
Contemporary painting
72
Posters
69
Works on paper
61
Design
55
Sculpture
48

## Slide 5
Milestones
Milestone
Target
Status
Contemporary painting batch
February 2026
Complete
Photography archive
January 2026
Complete
Works on paper, second tranche
November 2026
Scheduled
Design collection capture
December 2026
Scheduled
Phase 2 sign off and final report
31 March 2027
On track

## Slide 6
Next steps to close phase 2
• Hold throughput at 2,300 objects per month through the autumn
• Complete works on paper and design capture by the end of 2026
• Run the final quality audit and metadata reconciliation in early 2027
• Submit the EU partner sign off and final report by 31 March 2027

## Slide 7
Opening the collection to those who will never walk through the doors.
Digitisation Initiative, phase 2 review