## september CRs (reviewed)
CR | Request | Raised by | Vendor claim (Oct 7) | Observed in build 2.4.1 | Review verdict | Evidence required to close | Reviewer | Review date
CR-4 | Source dropdown mirrors the CRM lead sources | R. Whitfield | Included / done | Options changed: 'Bar Referral' -> 'Friend or colleague' (Website/Conference/Friend or colleague/Other) | NOT VERIFIED | CRM lead-source picklist; show dropdown matches it 1:1 | OpenClaw (for M. Brooks) | 2026-07-20
CR-5 | Response-time promise updated per the intake SLA | M. Brooks | Included / done | Footer changed 'five' -> 'ten business days' (looser promise) | NOT VERIFIED | Intake SLA document; confirm the exact target number | OpenClaw (for M. Brooks) | 2026-07-20
CR-6 | Pairing widget reads live from the CRM | D. Ortiz | Included / done | 'Pairings in Qualification' 9 -> 11, still under 'UAT preview: program stats' | NOT VERIFIED | Live demo / logged CRM API call; remove 'UAT preview' framing | OpenClaw (for M. Brooks) | 2026-07-20
CR-7 | Rename the Mentee label to Participant throughout | D. Ortiz | Included / done | UNCHANGED - section still reads 'Mentee information' (same as build 2.3) | NOT MET (FAIL) | Rename every 'Mentee' -> 'Participant'; re-screenshot | OpenClaw (for M. Brooks) | 2026-07-20
OVERALL REVIEW DISPOSITION: | NOT PASSED - do not go live Friday; return punch list to vendor (CR-7 fix + evidence for CR-4/5/6).
Acceptance reference: | September committee minutes (exact wording), CRM lead-source picklist, intake SLA.
Note: | Recordings audio_2.mp3 / audio_1.mp3 not transcribable (no whisper model on sidecar); verify exact targets against the minutes.