## Slide 1
EXHIBITION BOARD BRIEFING
Vienna Modern
Art and Society 1890 to 1930
Joyce Padilla, Director
Strategic plan progress, Q4 cycle, November 2026

## Slide 2
Agenda
• Exhibition at a glance, the headline numbers
• Budget allocation across the nine work lines
• Loan agreements and what remains open
• The road to opening night on 1 October 2026
• Risks, contingencies, and the board's decisions

## Slide 3
Exhibition at a glance
15
International loans
13 signed, 2 in talks
EUR 1.85m
Total budget
Nine work lines
1 Oct 2026
Opening gala
Federal Minister attends
1,200
Catalogue copies
Single print edition

## Slide 4
Budget allocation
Nine work lines, EUR 1,850,000 total
Loans, transport
420,000
Insurance
310,000
Install, design
250,000
Catalogue
220,000
Conservation
180,000
Marketing
160,000
Opening
140,000
Digital
90,000
Contingency
80,000

## Slide 5
Loan agreements
13 signed and confirmed
2 in talks
Combined insured value, EUR 48.7 million across the fifteen works.
The two open agreements, in Paris and New York, are in final negotiation with closure expected before the press preview.

## Slide 6
Road to opening
Date
Milestone
Owner
19 Oct 2026
First crates in transit
Conservation
22 Oct 2026
Budget consultation, ministry
Joyce Padilla
26 Oct 2026
Install begins in galleries
Margarethe Huber
1 Oct 2026
Opening gala and press
Director's office
8 Oct 2026
International press preview
Communications

## Slide 7
Risks and the board's decisions
• Two loans unsigned, contingency held at EUR 80,000 against late transport costs
• Press preview timing is tight, communications brief due three days ahead
• Decision sought, approval of the install schedule and the opening guest list
• Decision sought, sign off on the catalogue print run of 1,200 copies

## Slide 8
An argument about how a city sees itself.
Joyce Padilla, Director, Osterreichisches Kunstmuseum